## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Implement stability solver | 1 | 1 | 1 | 1 | 50%
Stability investigation and writeup | 2 | 2 |  |  | 0%
Non-gradient optimization setup and practise problem on pipe composite orientation | 4 | 3 |  |  | 0%
Writeup of theory and implementation of above | 7 | 1 |  |  | 0%
Extend optimisation to a more complicated example + writeup | 8 | 2 |  |  | 0%
Review report and submit to Andreas for checking | 10 | 1 |  |  | 0%
Prepare draft presentation and poster | 11 | 1 |  |  | 0%
Improve things based on feedback | 12 | 2 |  |  | 0%
Hand in report and hold presentation | 14 | 1 |  |  | 0%